## Sheet1
Team Members | Work Done Upto
| 7-Feb | 14-Feb | 21-Feb | 28-Feb
Sanchita Kasat | Setup flutter environment and learned basics of dart | Learned how to use layouts and widgets of Flutter | Integrating Google Maps API with Flutter geocoding
Anushka Chincholkar | Studied basic concepts of development in flutter | Developed basic app with flutter widgets and layouts | Studied basics of UI Design for Flutter
Atharva Kulkarni | Studied basics of dart and flashed LineageOS on old android smartphone for testing purposes
Shreya Sahni | 1. Studied syntax and other basics of dart, flutter 2. Set up flutter plugin with android studio | Continued learning and practising Dart, Flutter | Explored Firebase and learned how to integrate it with a Flutter application
Tejomay Padole | Flutter environment setup in android studio, started learning dart basics | Learnt how to incorporate images and custom fonts inside our flutter app, also tested out hot reload in flutter | Studied firebase and how to use it with flutter
Suruchi Shrey | Set up flutter environment and studied basics of dart | Made a basic app, learned using widgets and some gestures of flutter | Learned animation and state management in Flutter | Learned navigation and routing in flutter
Pradnya Kore | studied basics of dart and setup of flutter env | Learned how to work with widgets and other functionalities of Flutter
Sanskruti Nakhale | Learned Basics of Flutter and Dart | Flutter Learning Continued and Applying to make a basic app | Learned how to build layouts using Flutter’s layout mechanism. Learned widges Navigation and animation features